# Countryside Access Delivery Plan 2020- 2021

This plan is provided to advise on projects being implemented to deliver the Countryside Access Improvement Plan.  This plan will be amended and revised as projects and resources change.

| Well Maintained Public Rights of Way Network and Countryside Sites: To target improvements to ensure greatest public benefit is obtained. Objective: WM1 Better network/sites for leisure and daily use; WM2 Compliance; WM3 Promotion of responsible use; WM4 Evolution and increasing the accessibility of the network; WM5 Improve Green Infrastructure |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective and CAIP References | Description of activity | Lead Inc. delivery partners | Timescale | Status (Progress in italics) Q1 1st April to June 30th Q2 1ST July to 30 September Q3 1st October to 31 December Q4 January - April | Finance |
| WM1 1.1 Working with NFU/FUW/CLA & Landowners to reduce cropping issues | Cropping Ongoing cropping enforcement. (Expecting 10 Notices to be sent. 50+ inspections, 5 enforcement) Working with NFU/FUW/CLA to get cropping information out to landowners. You Tube videos possibly re standards. | MonLife Countryside Access | Ongoing from February 2020 Revised June ongoing | Q1 Covid & flooding both impacted on Project and flooding reduced spring crops significantly. Currently monitoring 30 cropping sites with repeated site visits. | Existing Officer resources |
| WM1 1.3 Improving general fingerpost and way marking to encourage use and build confidence prioritising areas within and near communities with high use As above | Project 1 Mark My Paths, Pilot Project for Wales. Training volunteers and identifying important missing fingerposts/signage. Then working with Communities, purchasing and installing identified posts Project 2 Living Levels Improvements to signage on key routes to the Wales Coast Path and development of best practice to do this. | MCC, Ramblers Cymru, Torfaen CBC Living Levels, MCC, MonLife Green Infrastructure, Newport Council, RSPB | January 2020 – March 2021 Q2 Installation expected of fingerposts Q3 Sign purchasing and installation Q4 | Publicity about campaign visit our webpage in March 2020. Q1 Covid has now stalled project. RA Cymru project officer furloughed. Q1 No work waiting confirmation of available budget | Existing Resources Living Levels £ to be confirmed |
| WM1 1.4 Prioritise and undertake bridge repairs and replacements. | Bridges -Prioritisation, Inspection and maintenance of Bridges | MonLife Countryside Access | Ongoing (Note Covid has stopped bridge replacement and maintenance in Q1) | Q1 Flood Inspections completed and WG notified of costs for repair. 4 bridges closed with legal order. 1 dangerous bridge at Drybridge park closed and will be removed July 2020. Other bridge work re-prioritised, 2 bridges (1 at Clytha and 1 at Tintern) and 1 boardwalk at Mathern waiting to be installed. 9 Bridges prioritised for purchase in q2. | Flood grant £? waiting confirmation Capital funding £25,930.44+ |
| WM1 1.6 Promote and provide better signed circular routes to increase confidence in wider use. | Promote and or sign Circular Routes - Working with The Narth Volunteer Group and the Penallt Volunteer Group to develop local circular routes - Development of a Geology circular walk, Cefn Ila, Usk - Living Levels three new circular routes. - Magor s106 Complete re-opening and promotion of 8 circular routes around Magor & Undy ( 2 of which are routes above) | MonLife CA Team The Narth, Penallt Volunteer Groups and Mon Life CA team RA Cymru, Llanbadoc CC, MonLife CA , WT, Gwent WT, MonLife, RSPB, Newport CC MonLife Magor & Undy CC | Ongoing May 2020 – May 2022 April 2021 Q2 Purchase Furniture to improve route for all Q4 Opening event and promotion April 2020 – March 2021 Autumn 2020 | Q1 All pathcare routes on Visitmonmouthshire website checked and re waymarked. Stay local message during lockdown meant unable to promote routes until public movement allowed. - Q1 Penallt Volunteer Group prioritising routes for promotion and works. Applying for grant funding - Q1 Geology route on hold due to Covid. - All materials purchased last year, new gates installed and waiting installation of way markers delayed due to Covid but expected Q2. Q1 No work | Existing budgets - £10,000 Access Grant - Access Grant £3,317 RA Cymru funding leaflet. - Living Levels £? - £4608 section 106 funding |
| WM1 1.10 maintain Offa’s Dyke Path National Trail and Wales Coast Path to agreed quality standards WM1 1.10 maintain Offa’s Dyke Path National Trail and Wales Coast Path to agreed quality standards | Sudbrook Fort Wales Coast Path - secure route and improve route over Hill Fort by building floating steps and carrying out surface/signage improvements | MonLife and Cadw | April 2020 –February 2021 | Site has been cleared and materials bought for physical works to start in April/May (subject to weather) Q1. On hold due to COVID | Part of costs below |
| WM1 1.10 maintain Offa’s Dyke Path National Trail and Wales Coast Path to agreed quality standards | Wales Coast Path General Maintenance ongoing - 2 cuts of vegetation - 2 bridges at St Pierre Golf Club and Pill Cottage to be installed Autumn 2020 - Checking and maintenance of gates/signage - Diversion to improve path at Mathern/St Pierre to resolve ongoing surface problems. | Natural Resources Wales, Welsh Government, MonLife Countryside Access | 1st April 2020 -31 May 2021 | Q1 Grant received June 2020, vegetation clearance contract in place | £14,964 NRW Grant of which 75% is funded and 25% match funded by MonLife. Additional £700 100% funded for diversion |
| WM1 1.10 maintain Offa’s Dyke Path National Trail and Wales Coast Path to agreed quality standards | Offa’s Dyke Maintenance Programme: - - Two cuts of vegetation & general maintenance - Replace gate at Llantillio Crossenny - 1 replacement directional finger post - 1 kit bridge - Winter route signage at Hendre/Abbey Bridge - Pathcare of route | NRW & MonLife | Ongoing April 2020 – March 2021 | Q1 Bid made Q2 1st vegetation cut to take place July 2020 | £8000 NRW Grant of which 75% is funded and 25% match funded by MCC Waiting for confirmation of grant letter |
| WM1. 1.11 Maintain regionally promoted routes to a high standard seeking stronger invigorated regional partnerships along whole lengths to ensure maximum public benefits | Wye Valley Walk bank/erosion project in Monmouth Maintain Wye Valley Walk Partnership (new website, setting up of Friends Group etc.) | Wye Valley AONB Project Officer, MonLife CA |  | Q1 New project officer, considering design for improvements to protect river bank and WVW at Monmouth. Also seeking grant for improvements to walk and Cleddon Shoots. | AONB reserves £35K |
| WM1 1.12 Maintain countryside sites and prepare management plans for each site. | Produce Site Management Plans. Improve surfacing/access at Castle Meadows Consider new site management regimes in light of Covid | MonLife GI & CA MonLife Countryside Access MonLife Countryside Access | ENRaW funding 19/20 completed 20/21 (tbc) 21/22 (tbc) 22/23 (tbc) 2020-2022 March 2020 ongoing | - Castle Meadows - completed plan ( review 22) - Caldicot Castle - completed plan (review 22) - Goytre Hall –completed/under review - Black Rock – completed/under review - Abergavenny Castle completed/under review GF - Warren Slade - - Completed under review - Old Station – Completed/under review GF– - Rogiet Country Park – proposed | Grant Funding ENRaW - 2022 ENRAW 2022 ENRAW 2021 ENRAW 2020 ENRAW 2021 ENRAW 2020 ENRAW 2020 ENRAW 2020 ENRAW 2020 Active Travel/Capital funding TBC |
| WM1 1.12 Maintain countryside sites and prepare management plans for each site. | Clydach/ CEMEX site Development Rogiet Countryside Park Car Park | BBNPA, RR, CB, ML MCL/ KS/ ML Highways CB | TAIS grant + section 106 By March 2021 To be determined | Q1 no progress due to Covid Current programme tbc |  |
| WM3. Promote the countryside code and responsible use by the public particularly dog ownership and England/Wales /Dog Walking Code. | Promotion of countryside code through social media and websites and where other opportunities arise Promoting the MonLife “Caring for the countryside” workshop to local schools. | MonLife | ongoing | Q1 Dog Code in Covid page. Development of destination management & countryside access recovery plan from Covid, which includes messages about responsible behaviour. Agreed across MonLife for publication from June 2020. New countryside code pending from WG. |  |
| WM3 3.1 “Provide advice and guidance to landowners regarding PROW responsibilities.” | Enforcement/Maintenance Advice & guidance to Landowners - Update and promote Countryside Access Policy, Protocol and Operational Management. Timescale by July 2020 - Improve information available on website. - Staff to give advice on site |  | July 2020 ongoing | Q1 Countryside Access Policy, Protocol and Operational Management Guide endorsed by Cabinet. | Existing resources |
| WM4 4.0 Continue to uphold Least Restrictive Access Policy and seek removal of other barriers to use such as steps and narrow gates. | Least Restrictive Access - Identifying opportunities to improve access and give advice to volunteer groups/ community and others re LRA where required. |  | Ongoing | Q1 Gates purchased in 2019 by Llanvapley volunteers to replace 30 stiles with gates. Installation on hold due to Covid Opportunity to improve access in Penallt identified and being explored. | Funding obtained by CPRW bid to solar farm community fund Access Grant (waiting for confirmation of funding) |
| WM4 4.2 Provide more, short, circular promoted routes for health, leisure and tourism | See also WM1 1.6 & CI1 18.1 Circular route development | MonLife CA, Penallt Volunteer Group, Ramblers Cymru, MonLife CA & GI, Llanbadoc CC, Living Levels |  | Q1. Funding identified and applied for route development in Penallt, Geology Walk in Llanbadoc, route in Llansoy and 8 routes in Magor & Undy. Waiting approval of grants. | Access Grant & section 106 funding |
| WM5 5.0 Work with planners/developers to create planned strategic green infrastructure which incorporates the PROW network to promote and encourage sustainable active travel and provide opportunities for recreation and leisure. | Advice to planners / developers to create strategic green infrastructure access improvements | Mon Life GI | Ongoing | Suggestions totalling £50k to MCC planners in Q1 in response to request for ideas for a potential new S106 for new proposed development in Magor. | Existing resources |
| WM 6.3 Identify and support measures that will reduce traffic speed and volume where this will preserve or improve network connectivity for non-motorised users. | Active Travel route and highway improvements | Highways, NT, Cadw, BBNP, | May onwards | Q1 Covid has seen many places with reduced traffic and an increase in active travel/recreation. MCC consulting on what measures could be put in place as lockdown reduces to keep active travel routes and people safe. Identification of improvements within towns and villages and discussion about potential long term improvements to reduce speeds and traffic on going. |  |
| Active Healthy Lifestyles: To improve the accessibility of the network/countryside sites and to make it easier for people to incorporate walking, riding and cycling into their everyday lives. To support the rights of way network for purposeful journeys. Objectives: - Increase Health and Well Being Benefits; Active Travel; Modal shift to walking & cycling; Tackling deprivation and disadvantage |  |  |  |  |  |
| Objective and CAIP reference | Description of activity | Lead Inc. delivery partners | Timescale | Status Q1 1st April to June 30th Q2 1ST July to 30 September Q3 1st October to 31 December Q4 January - April | Finance |
| AHL1 7.0 Target priority areas and deliver improvements to the network and sites addressing health inequalities through increasing active travel and recreational activity. Also 8.4 Remove barriers to active travel and recreation and promote routes and opportunities | Active Travel Monmouth Improve and extend surfacing from Monmouth, Rowing Club to Dixton Church. New signage for blind and others and also improved boardwalks making route more accessible to all and providing active travel link to church and school. | MonLife | 2020/22 | Q1Active Travel Bid made. Comments made on Cycling Strategy and new INMS maps. | Active Travel bid made and not yet confirmed |
| As above AHL1 7.0 Also 8.4 | Active Travel Castle Meadows, Abergavenny upgrade all paths on Castle Meadows site with a surface to resist flooding and improve active travel opportunities | MonLife Countryside Access | 2020/22 | Q1 Active Travel bid made | Active Travel Bid made but not yet confirmed |
| AHL1 7.0 Target priority areas and deliver improvements to the network and sites addressing health inequalities through increasing active travel and recreational activity. | Usk Railway Path Creation of cycle way | MCC Highways | 2020/21 | Q1 Lead being taken over by the Highways Projects team as an 20/21 Active Travel bid | Funding not confirmed (20/21 AT bid) |
| AHL1. 7.2 Support volunteering on sites and rights of way and seek opportunities for specific groups to also enhance access on permissive paths on NRW land. | Penallt Volunteer Group Promotion of new circular route (Buzzard). Negotiation/consultation with NRW by MonLife CAT team re permissive route. | The Narth Volunteer Group, Mon Life Countryside Access and NRW | June 2020 - 2021 | Q1 Volunteering stopped due to Covid Q2July - consultation to take place with NRW re new permissive route at Troy Park Wood | Existing Resources |
| AHL1 7.3 Work with partners to support implementation of health improvement initiatives, such as Fit4Life Groups, Walking for Health, cycling and walking initiatives and GP referral. | Dementia Walks Follow on from pilot project in 2019/20. Dementia training for staff and volunteers. Identification of improvements on countryside sites and linking PROW that would help support Dementia Walks programme. Promotion through Health Board and GP surgeries. | Karin/Ruth/Mark | April 2020- 2022 | On hold because of Covid |  |
| AHL 1 7.9 In conjunction with partners look at installing & maintaining picnic benches/seats to enable more use of sites/PROW for those with disability or health issues. | Consideration of existing and new furniture requirements on sites to take place in conjunction with consultation on site management plans, active travel projects and Dementia Project | Local Health Groups/ Disabled Ramblers, Local Health Board, Friends of Groups, Volunteer Groups, U3A Groups, Monmouthshire LAF | April 2020 – March 2021 | On hold due to Covid | Existing resources |
| AHL2 8.4 Support and Influence the authorities and other strategies and policies to ensure that active travel is firmly integrated into work programmes. | Comment on draft plans, policies and strategies regarding active travel | MonLife | Ongoing | Q1 Active Travel Bids made. Assistance with Active Travel Map consultation and input | Existing resources |
| Knowing What’s Out There: To achieve an up-to-date and accessible Definitive Map and Statement and to promote countryside sites and PROW network. Objectives; Maintain and make more accessible records; Provide advice on PROW network & countryside sites; Negotiate Improvements; More accessible information/increasing knowledge and confidence; Promotion of Wales Coast Path, Offa’s Dyke National Trail & promoted routes; Sustainable tourism; Disability promotion improvements |  |  |  |  |  |
| Objective and CAIP Reference | Description of activity | Lead Inc. delivery partners | Timescale | Status Q1 1st April to June 30th Q2 1ST July to 30 September Q3 1st October to 31 December Q4 January - April | Finance |
| KWOT 11.2 Maintain pubic registers on line and add list of all section 147 authorisations and legal orders | List of section 147 authorisations being produced List of Legal Orders (Diversions/Creations) being created for inclusion on website. List of temporary closures updated | MonLife Countryside Access | Q3 October 2020 | Q1 S147 and Legal orders register prepared needs checking and updates Temporary closures on line here | Existing resources |
| KWOT 11.3 Continue to process claims according to prioritisation and seek additional resources to clear backlog of applications. | Process Modification Applications | MonLife Countryside access, Legal Services, Highways, Planning Inspectorate | Ongoing (Note unable to make orders, or go to committee during Covid lockdown) | Q1Currently 43 DMMO applications on the WCA 1981 s.53B Register including 1 new assessed claim at Lady Hill, Usk. Advice ongoing as required to landowners/public etc. Priority cases 1, 2 (routes A and B), 5 & 6 are at committee stage. Delay due to Covid. Waiting for committee to be working again. Priority 3 Price’s Bridge 01 13Mod with legal 14th Jan 2020, to be sent to PINS for Public Inquiry Gt Panta, Devauden. Public Inquiry postponed and now being dealt with by written representation by Planning Inspectorate who advised on 17/06/2020 that modification order should be re-consulted upon as part footpath and part restricted byway. Order to be re-advertised | Existing resources |
| KWOT2 12.1 Liaise with Planning and Development management to provide advice on Local Development Plan and planning applications. | Advice re policies for Local Development Plan ongoing Ongoing advice re planning applications | MonLife Countryside Access | Ongoing | LDP consultation postponed due to Covid (Q1 23 planning applications made comment on.) |  |
| KWOT2 Respond to and give advice to Land Charge searches. | Responding to land charge searches | MonLife Countryside Access | ongoing | Q1 responded to 108 searches |  |
| KWOT2 Advise on and where appropriate progress orders to amend the public right of way network in the interests of the public and or landowner. | Processing applications to create, move, or close public paths. | MonLife Countryside Access | ongoing | Q1 11 applications in progress of which 3 are Town and Country Planning Act Orders and 7 are Highways Act Orders. 1 Rail Crossing Order 4 pre –order consultations taken place 6 waiting for order to be made 1 waiting to go to committee 1 waiting confirmation 1 waiting certification 1 new application (Wales Coast Path) | Existing resources and X agreements with applicants to pay costs |
| KWOT2 12.4 Provide advice and where appropriate progress orders for temporary closures but with conditions as per policy. | Process and make temporary closure notices as required | MonLife Countryside Access | ongoing | Q1 Flooding in February resulted in 4 temp closure notices. Other temporary closure orders made as per register. |  |
| KWOT2 12.5 Consider developing policy for requests to plant trees, install seats/plaques etc. in country parks/sites | Develop policy for sites regarding bereavement requests/donations for trees etc. | MonLife | Q4 | New |  |
| KWOT3 13.1 Work with NRW to review access on their sites, reduce modification claims and produce management plans that can help inform future tree clearance programmes, reducing access closures and assisting with aims in 13.0 | Work with NRW reviewing other ways of dealing with claims on NRW land and seek resources to produce management plans. | NRW, MonLife | ongoing | No progress Q1 |  |
| KWOT4 14.4 Work with NRW & other woodland partners to provide better information about what access is available in woodlands | Woodland Access Information Provide links to NRW’s sites on MonLife’s webpages and Visit Monmouthshire | NRW, MonLife Destination Management and Countryside Access | October 2020 | Not yet started due to Covid |  |
| KWOT4 14.5 Encourage NRW TO provide and share an easily accessible map showing the extent of Welsh Government woodland estate that is subject to permissive access by horse riders. | Bridleway Access Information in Woodlands Establish where the public can ride a horse in NRW woodlands within Monmouthshire and make information accessible | NRW, MonLife Destination Management and Countryside Access | December 2020 |  |  |
| KWOT5 15.1 Maintain primary promoted routes to a high standard to safeguard economic benefits and tourism product | Ongoing maintenance programmes for regional routes Wye Valley Walk / Overlooking the Wye Walks | MonLife Countryside Access AONB |  | Q1 Cutting programme in place for all regional routes Input into delivery of wye valley walk website revamp, waymarking, new guide and republishing OTW walks – include resolving Llandogo route. | AONB funded 19/20 |
| KWOT5 16.0 provide information to help support community led tourism | Living Levels (Destination marketing/signage, levels festival) |  | 2020/21 Q2 | Q1 No work |  |
| KWOT 16.2 Refresh and Improve signage to and in countryside sites | Review of signage across MonLife sites | MonLife Countryside Access |  | Q1 New entrance signage for Covid June 2020 |  |
| KWOT6. 16.3 More guided walks and events | Events/Guided Walks | MonLife Countryside Access | 2 guided walks planned each month in 2020/21 | On hold due to Covid |  |
| Community Involvement: To support and enable volunteer groups to be actively involved with countryside projects, contributing to well-being and creating sustainable and resilient communities. Objectives:- Volunteer Involvement; Assisting volunteers; New volunteer programmes to improve health and well-being, improve environment/biodiversity and get young people volunteering |  |  |  |  |  |
| Objective and CAIP Reference | Description of activity | Lead Inc. delivery partners | Timescale | Status Q1 1st April to June 30th Q2 1ST July to 30 September Q3 1st October to 31 December Q4 January - April | Finance |
| CI1 18.1 Support existing groups and the development of new community groups to improve and maintain their local rights of way and countryside sites | Supporting Volunteers, Friends Groups Local Ways Groups & Community Groups. | MonLife Countryside Access Ramblers Cymru Volunteer Groups Community and Town Councils | Ongoing | Q1 Ongoing advice to various groups and some potential new recruits found. (11 groups and 72 direct volunteers) Potentially 3 new groups Training on Safeguarding, first aid, manual handling, guided walk leaders, brush cutter, pathcare for individuals and groups, supervisor training for group leaders as required. On hold for Covid MonLife Awards. Network meetings for path groups, Guided walk leaders meeting. MonLife Volunteer Newsletter. MonLife Quiz night. |  |
| CI1 18.1 Support existing groups and the development of new community groups to improve and maintain their local rights of way and countryside sites | Supporting Monmouthshire Local Access Forum | MonLife, NRW, WG | ongoing | Q1 New LAF awaiting first meeting, election of chairman and to finalise 19/20 report. On hold all meetings until change of legislation made to allow alternative meeting arrangements during Covid. 1 update provided to LAF Members. |  |
| CI1 18.2 Develop guidance, training and promotional material to help educate and attract volunteers | Development and updating of information to help countryside access volunteers | MonLife Countryside Access | ? | Q1 Established MonLife volunteer webpage. New check lists for Walk Leaders and Pathcare Volunteers |  |
| CI2 19.0 Improve Information Technology and mapping interface to be more useful for volunteer projects | Improving CAMS web | MonLife Countryside Access Exegesis SRS Newport Information Hub | January 2021 | Q1 Contract in place to update website to meet security, accessibility and welsh language standards. Add additional functionality to include support volunteers, additional workflows for officers, e.g. bridge assessments and improve speed and base mapping provision. |  |
| C12 19.1 Develop and publish guidance on responsibilities for groups and insurance requirements | Producing guidance for volunteer groups | MonLife Countryside Access | April 2020 –December 2021 | Q1 Completed guidance for using power tools. |  |
| CI2 19.2 Identify method of collating and giving information on grants to community and other groups | Compile method of collating and giving information on grants to community and other groups | MonLife | Q3-4 |  |  |
| A Prosperous Wales: To maximise the economic benefits of countryside access Objectives: To maximise economic benefits, Improve product and grow new markets |  |  |  |  |  |
| Objective and CAIP Reference | Description of activity | Lead Inc. delivery partners | Timescale | Status Q1 1st April to June 30th Q2 1ST July to 30 September Q3 1st October to 31 December Q4 January - April | Finance |
| FW1 21.3 Continue to work in partnership with other coastal authorities, NRW, WG and others to secure improvements to WCP and maintain to quality standard | Maintain Regional Coast Path Management Meetings | NRW, WG, CADW, MonLife | ongoing | Q1 Regular updates re covid situation and grant applied for Regional Meeting 01/06/2020 | WCP grant £15644 |
| Future Focused: Working for a resilient and future focused service in partnership with others, to provide wider benefits to residents and visitors in Monmouthshire. Objectives:- Increase awareness of the CAIP, Links to other strategies and plans; To deliver objectives in the plan; Partnership working; Environmental Impact & Mitigation Measures; Resourcing; Improved customer service; Legislative changes & operational management |  |  |  |  |  |
| Objective and CAIP Reference | Description of activity | Lead Inc. delivery partners | Timescale | Status Q1 1st April to June 30th Q2 1ST July to 30 September Q3 1st October to 31 December Q4 January - April | Finance |
| FF1 22.0 Raise awareness pf the ROWIP to customers, non- users of the network and stakeholders. | Promotion of CAIP | MonLife, WG & NRW, Monmouthshire LAF | ongoing | Q1 Promotion of final CAIP. Delayed due to covid Q2 Update website, local press social media campaign. 300+ Emails to stakeholders. | Existing resources |
| 23.0 Strengthen partnership working with key Stakeholders to make better sense of the network and provide well-maintained safe attractive environments. | Working with Highways and other partners in developing active travel routes Production of information to community councils | MonLife and all key stakeholders | ongoing | Q2 Developing improvement scheme with Canals and Rivers Trust and BBNP. Working with Highways and National Trust in developing active travel routes around important sites like the Sugar Loaf in Abergavenny. | Existing resources |
| FF4 24.2 Identify flood risk areas and likely impact on PROW. Put in place mitigation measures. Seek alternative routes for those parts of Offa’s Dyke Path National Trail and regional routes prone to flooding. | Flooding Impact Identify impact of flooding on prow . |  | ongoing | Q1 Assessments from Feb to end April 2020. Flood maps overlaid with CAMS data to consider impacts and opportunities Flood assessment data provided to WG | Waiting for confirmation on flood repair grant from WG |
| FF5 25.0 Resourcing – Ensure adequate resources for funding of CAIP by securing additional resources from internal and external sources that help achieve the objectives within this plan. | Grant application and resources | MonLife Countryside Access and GI | Ongoing | Q1 - Active Travel Bids made and waiting confirmation - £300,000+ Flooding assessment and evidence passed to WG Waiting to hear re grant - Bids and grants received for Offa’s Dyke Path National Trail and Wales Coast Path. - Bid made for ENRaW grant funding in conjunction with Greater Gwent CCs. Waiting to hear if successful. - GI funding for Warren Slade woodland management and Clydach Ironworks approved - New WG Access Grant – pending confirmation |  |
| FF5 25.3 Seek to maintain and improve the delivery of the countryside access service through charging for activity where admissible | Review of existing charges and where new income could be made |  |  | Q1 Identification of need to raise additional £10k+ revenue |  |
| FF5 26.2 Provide updates about specific improvements to user groups | Identify needs for updates Provide register of legal orders on-line Build in method for grant work of reporting progress to user groups | MonLife and stakeholders | ongoing | Q1 Registers see KWOT 11.3 Knowing what’s out there Q2 Delivery Plan available on line |  |
| Ff6 26.0 Provide the customer with a range of methods of reporting an issue | Improve Websites re how to report an issue, consider adding information on signs like finger posts. Social media and press campaign. Email update to volunteers and user groups. | MonLife Countryside Access | Autumn/Winter 2020 | Q2 Update MonLife Website |  |
| FF7 27.1 Review operational policies and priorities in light of the CAIP implementation | Ongoing review of operational policies | MonLife Countryside Access | Ongoing (Expected in Q2 Review of modification order policy and for use of drones on countryside access sites. Q3 Review of funding and policy for naming row) | Q1 Operational management guide produced, Review of Fishing Agreement on Castle Meadows completed and new policy in place for benches |  |
| FF27.2 Periodically review operational policies in response to legislative change. | Create Risk Assessment approach, and operational procedures for new Covid Regulation Closures Consultee on Welsh Government proposals for legislative change |  | ongoing | Q1 Risk Assessment Matrix approach, design for orders etc. all complete and being actioned. Web site updated with info for Covid. Comments made on new legislative options for communicating access rights, CRoW Access Changes and PROW Flexibility. |  |
| FF7 27.3 Provide PROW officers and volunteers with necessary training to ensure effective delivery of PROW operation. | Training for effective delivery (Dementia Training, CAT scanners, QTRA training, manual handling, CAMS upgrade, Least Restrictive Access) |  | ongoing | Staff Q1 - Covid Training - Anti-terrorist training - Manual Handling Volunteers training on hold |  |

Key Performance Indicators

| Indicator | Actual 2018/19 | Target 2019/20 | Actual 2019/20 | Target 2020/21 | Actual 2020/21 Q1 | Actual 2020/21 Q2 | Actual 2020/21 Q3 | Actual 2020/21 Q4 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Countryside Access Volunteer hours (direct volunteers) | 3089.5 +1326 recorded indirect (1) | 3,000 | 3294 Direct 2265.5 Indirect 1028.5 | 2,000 | Direct 69 Indirect 6 |  |  |  | Note 1: partial recording only. All volunteering stopped in Q1 due to covid so expect results to be lower this year |
| Countryside Access Indirect volunteering groups supported) | 13 | 15 | 11 | 12 | 11 |  |  |  |  |
| Resolved ROW enforcement issues in year | 1648 |  | 1750 |  |  |  |  |  |  |
| Unresolved ROW enforcement issues | 1339 |  | 1365 |  |  |  |  |  |  |
| Percentage of ROW enforcements issues resolved (cumulative) | 55.17 | 56% | 56.18% | 50% |  |  |  |  | PI’s% for 2020/21 lower due to covid restrictions |
| Resolved ROW maintenance issues in year | 6594 |  | 6971 |  |  |  |  |  |  |
| Unresolved ROW maintenance issues | 3370 |  | 3592 |  |  |  |  |  |  |
| Percentage of ROW maintenance issues resolved (cumulative) | 66.18 | 65% | 65.99% | 55% |  |  |  |  | PI’s% for 2020/21 lower due to covid restrictions |
| Green Flag Award status awarded/maintained | 3 | 3 | 3 | 3 |  |  |  |  | Annual assessment of selected sites through annual applications (currently 3) |